## Plan
Week1 | Requirements Analysis & High-Level Design | 10
Day 1& 2 | Requirement Gathering & System Analysis | 4
Task 1 | Identify Functional Requirements
Define the core functions of the project
FRAM read/write operations
Communication protocols: I2C/SPI for interfacing the STM32 with FRAM.
Debugging through UART
Power management, using sleep modes in STM32 to minimize power usage
Task 2 | Identify Non-functional Requirements
Determine performance requirements such as read/write speed, data retention, and power consumption
Establish limitations such as the memory size of FRAM and STM32 resources (flash memory, RAM).
Deliverables: Detailed requirements document (functional and non-functional), outlining the memory access protocols, debugging, and power management features.
Day 3: | Use Case Development | 2
Task 3 | Develop Key Use Cases
Define key scenarios:
Writing a block of data to FRAM.
Reading the data from a specific address in FRAM.
Entering and exiting low-power modes.
Debugging through UART, including logging memory operations and power status.
Deliverables: Use case document with flow diagrams outlining scenarios such as normal operations, error handling, and power management.
Day 4-5 | High-Level System Design
Task 4 | Create System Architecture Diagram
Develop a high-level architecture showing:
STM32 controller.
FRAM connected via I2C/SPI.
UART for communication and debugging.
Power module managing low-power modes.
Define the data flow between components, highlighting how data will be written/read from FRAM and the process for logging events over UART.
Task 5 | Block Diagram of Subsystems
Subdivide the system into smaller blocks like communication (I2C/SPI), memory management (FRAM), debugging (UART), and power management.
Define key responsibilities of each block.
Deliverables: High-level system architecture diagram and detailed block diagrams of each subsystem.

## Functional Requirements
Functional Requirements (Expanded)
1.1. Memory Operations (FRAM Read/Write)
| • | Basic Write Operation:
| • | STM32 must initiate a write sequence to store a single byte, word, or a block of data at a specific memory address in the FRAM.
| • | System should verify the memory address to ensure it’s within the valid address range (e.g., 0x0000 to 0xFFFF for 64Kb FRAM).
| • | After writing, STM32 should confirm the write operation via status check (FRAM acknowledgment signal, completion flag).
| • | Advanced Write Operation:
| • | Support for writing large data blocks that span multiple FRAM pages, requiring address wrapping and chunk-wise writing.
| • | Implement write-protection mechanisms: allow certain sections of memory to be protected against overwrites unless explicitly unlocked.
| • | Basic Read Operation:
| • | The system should initiate a read sequence to fetch a single byte, word, or block of data from a specific memory address in the FRAM.
| • | After reading, STM32 should verify the data (e.g., through checksums or parity bits) to ensure data integrity.
| • | Advanced Read Operation:
| • | Support for reading large data blocks by sequentially fetching data across multiple memory addresses and returning it in a contiguous buffer.
| • | Implement partial read capabilities: allow selective reading of specific bits/bytes within a word or block of memory.
| • | Erase Operation (Optional):
| • | Although FRAM is non-volatile and doesn’t require erasing, the system could support a feature that clears specific memory blocks (set all bits to 0 or 1).
1.2. Communication Protocol (I2C/SPI)
| • | Initialization and Configuration:
| • | During system startup, STM32 should configure I2C or SPI interface with user-defined parameters:
| • | Clock speed (e.g., 100kHz for I2C standard mode, 1MHz for SPI).
| • | Addressing mode (7-bit or 10-bit I2C addresses, or byte vs. block addressing for SPI).
| • | FRAM device initialization: check that the device is present and responding on the I2C/SPI bus.
| • | Communication Logic:
| • | I2C/SPI functions should be modular and reusable across multiple projects:
| • | Functions like init_I2C(), read_FRAM(uint16_t address), and write_FRAM(uint16_t address, uint8_t data) should abstract the communication logic.
| • | Address mapping should support both linear (byte) addressing and block-based addressing, depending on FRAM size.
| • | Error Handling for Communication:
| • | Handle communication errors like no acknowledgment (NAK) from the FRAM, bus errors, or timeouts during data transmission.
| • | Implement retry mechanisms if the STM32 fails to establish communication with the FRAM (e.g., retry up to 3 times before giving an error).
| • | Error recovery: If an error occurs, reset the I2C/SPI interface or restart the communication.
| • | Protocol Options:
| • | I2C: Addressing scheme should support 7-bit or 10-bit addressing mode, clock stretching support, and multi-master mode (if applicable).
| • | SPI: Full-duplex communication, adjustable clock polarity (CPOL) and clock phase (CPHA), and different data frame formats (8-bit, 16-bit).
1.3. Data Integrity and Error Handling
| • | Checksum or CRC:
| • | For critical data, implement checksums or Cyclic Redundancy Check (CRC) to ensure the data has been correctly written or read.
| • | Include error detection algorithms to verify that no data corruption has occurred.
| • | Error Handling Strategy:
| • | Detect common errors like:
| • | Incorrect address access (trying to access an invalid address).
| • | Communication errors (device not found, no response from FRAM).
| • | Memory overflow: trying to write beyond the available FRAM size.
| • | When an error occurs, trigger an error message via UART for debugging.
| • | Error Recovery:
| • | Retry failed write/read operations up to a pre-defined limit.
| • | If error persists, log the error via UART and halt or move the system into a safe state (e.g., reset communication bus).
1.4. UART Debugging
| • | Initialization and Configuration:
| • | The UART should be initialized at the start of the program with user-configurable baud rate (e.g., 9600 or 115200 bps).
| • | Configure parity, stop bits, and data format (8N1 or 7E1).
| • | Debug Messages:
| • | General Format: Each message should follow a standard format like [INFO], [ERROR], or [DEBUG] to categorize the log.
| • | Success Messages:
| • | E.g., [INFO] Data successfully written to address 0x1234 after a write operation.
| • | Error Messages:
| • | E.g., [ERROR] Write operation failed at address 0x5678 if the write fails due to no acknowledgment from FRAM.
| • | Runtime Statistics Logging:
| • | Log system performance details like total read/write operations, system uptime, and power mode transitions.
| • | Diagnostic Data:
| • | Allow the developer to trigger diagnostic logs (e.g., sending real-time memory content or peripheral status over UART).
1.5. Power Management
| • | Low-Power Mode Activation:
| • | The system should enter low-power modes (e.g., STOP, SLEEP, or STANDBY) when no read/write operations are pending.
| • | Low-power modes should be enabled by default after initialization.
| • | Wake-Up Sources:
| • | Define interrupt-driven wake-up sources, such as:
| • | External pin interrupts (e.g., a button press).
| • | Communication wake-up: an I2C/SPI or UART activity can wake up the system.
| • | Timer-based wake-up to periodically check FRAM or perform maintenance tasks.
| • | Dynamic Power Scaling:
| • | Dynamically scale the clock speed or peripherals power usage based on system requirements (e.g., scale down the clock when only UART is active).
1.6. Addressing and Data Storage
| • | Address Mapping:
| • | Define address map for FRAM based on the size of the memory module (e.g., 64KB).
| • | The addressing scheme should be flexible enough to support future expansion if larger FRAM is used (e.g., 128KB or more).
| • | Data Organization:
| • | Data should be categorized into different regions based on importance:
| • | Critical data (configurations, system state) should be stored in protected regions.
| • | Non-critical data (logs, temporary data) can be stored in general-purpose regions.
Functional Requirements:
| 1. | Memory Operations (detailed write/read operations, error handling).
| 2. | Communication Protocols (I2C/SPI configuration and communication logic).
| 3. | Data Integrity (checksum, CRC, error recovery).
| 4. | UART Debugging (real-time logging and debug messages).
| 5. | Power Management (low-power modes, wake-up sources).
| 6. | Addressing and Data Storage (address map, data categories).
Requirement ID | Requirement Type | Requirement | Corner Cases Considered
FRAM_FUNC_001 | Functional | FRAM should communicate with STM32 over SPI or I2C protocol, ensuring compatibility with multiple FRAM models. | Bus contention, FRAM power failure during communication, support for multiple FRAM models.
FRAM_FUNC_002 | Functional | Data read/write operations should be reliable and able to handle both standard and corner cases like interrupted transactions or partial writes. | Handling communication failures, ensuring data integrity during mid-transaction failures, and managing partial data writes.
FRAM_FUNC_003 | Functional | STM32 should initialize the FRAM with correct configurations at startup, checking for power stability and proper reset conditions. | Ensuring proper system reset after unexpected power loss, checking proper voltage levels before initialization.
FRAM_FUNC_004 | Functional | Error handling should cover scenarios such as bus collisions, incorrect timing, or voltage drops, with retry mechanisms. | Handling SPI/I2C bus errors such as noise, incorrect clock rates, and voltage mismatches with retries and error logs.
FRAM_FUNC_005 | Functional | The interface should allow for both byte-level and block-level data transfers, including burst mode and handling large data with flow control. | Handling continuous data transfer for large datasets, flow control for slow FRAM responses, and buffer overflow handling.
This detailed plan should provide a solid foundation for the successful development of your STM32 and FRAM project, ensuring both the system’s functionality and robustness.

## Fun_Req
Requirement ID | Requirement Category | Requirement Description
FRAM_FUNC_001 | Memory Operations | Basic Write Operation: STM32 must initiate a write sequence to store a single byte, word, or a block of data at a specific memory address in the FRAM.
FRAM_FUNC_002 | Memory Operations | System should verify the memory address to ensure it’s within the valid address range (e.g., 0x0000 to 0xFFFF for 64Kb FRAM).
FRAM_FUNC_003 | Memory Operations | After writing, STM32 should confirm the write operation via status check (FRAM acknowledgment signal, completion flag).
FRAM_FUNC_004 | Memory Operations | Support for writing large data blocks that span multiple FRAM pages, requiring address wrapping and chunk-wise writing.
FRAM_FUNC_005 | Memory Operations | Implement write-protection mechanisms: allow certain sections of memory to be protected against overwrites unless explicitly unlocked.
FRAM_COMM_001 | Communication Protocol | Initialization: STM32 should configure I2C/SPI interface with user-defined parameters like clock speed, addressing mode, etc.
FRAM_COMM_002 | Communication Protocol | Communication Logic: Implement functions like init_I2C(), read_FRAM(uint16_t address), and write_FRAM(uint16_t address, uint8_t data).
FRAM_COMM_003 | Communication Protocol | Address mapping should support both linear (byte) addressing and block-based addressing, depending on FRAM size.
FRAM_COMM_004 | Communication Protocol | Error Handling: Handle communication errors like no acknowledgment (NAK) from the FRAM, bus errors, or timeouts.
FRAM_COMM_005 | Communication Protocol | I2C/SPI Protocol Options: I2C addressing scheme should support 7/10-bit modes. SPI: Full-duplex, adjustable clock polarity (CPOL/CPHA).
FRAM_DATA_INT_001 | Data Integrity and Error Handling | Checksum or CRC: For critical data, implement checksums or Cyclic Redundancy Check (CRC) to ensure data integrity.
FRAM_DATA_INT_002 | Data Integrity and Error Handling | Error Handling Strategy: Detect common errors like incorrect address access, communication errors, or memory overflow.
FRAM_DATA_INT_003 | Data Integrity and Error Handling | Error Recovery: Retry failed write/read operations up to a pre-defined limit and log the error via UART if the error persists.
FRAM_UART_001 | UART Debugging | UART Initialization: The UART should be initialized at the start of the program with user-configurable baud rate and format settings.
FRAM_UART_002 | UART Debugging | Debug Messages: Messages should follow a standard format like [INFO], [ERROR], or [DEBUG] to categorize the log.
FRAM_UART_003 | UART Debugging | Success Messages: E.g., [INFO] Data successfully written to address 0x1234 after a write operation.
FRAM_UART_004 | UART Debugging | Error Messages: E.g., [ERROR] Write operation failed at address 0x5678 due to no acknowledgment from FRAM.
FRAM_PWR_MGMT_001 | Power Management | Low-Power Mode Activation: The system should enter low-power modes (e.g., STOP, SLEEP) when no read/write operations are pending.
FRAM_PWR_MGMT_002 | Power Management | Wake-Up Sources: Define interrupt-driven wake-up sources, such as external pin interrupts or communication activity.
FRAM_PWR_MGMT_003 | Power Management | Dynamic Power Scaling: Dynamically scale the clock speed or peripherals power usage based on system requirements.
FRAM_PWR_MGMT_004 | Power Management | Timer-based wake-up to periodically check FRAM or perform maintenance tasks.
FRAM_ADDR_DATA_001 | Addressing and Data Storage | Address Mapping: Define address map for FRAM based on the size of the memory module (e.g., 64KB).
FRAM_ADDR_DATA_002 | Addressing and Data Storage | Data Organization: Critical data should be stored in protected regions. Non-critical data can be stored in general-purpose regions.
FRAM_ADDR_DATA_003 | Addressing and Data Storage | Flexible addressing scheme should support future FRAM expansion (e.g., 128KB or more).

## Non-Func_Req
Requirement ID | Requirement Type | Requirement | Corner Cases Considered
FRAM_NONFUNC_001 | Non-Functional | The interface should ensure data integrity during transmission, with checksums or CRC verification for every transaction. | Data verification even in cases of interrupted transactions or environmental disruptions during transfer.
FRAM_NONFUNC_002 | Non-Functional | Power consumption should be minimized, with the system going into low-power modes during idle communication periods. | Minimizing power draw during standby and ensuring smooth transition between active and idle states.
FRAM_NONFUNC_003 | Non-Functional | The communication speed should be adaptable, allowing for dynamic scaling based on system load or environmental factors (e.g., temperature or voltage). | Adapting communication speed based on system temperature, voltage variations, or workload for optimal performance.
FRAM_NONFUNC_004 | Non-Functional | The system should remain reliable under harsh conditions like temperature extremes, power fluctuations, or high EMI environments. | Handling extreme temperatures, power spikes, and ensuring reliability in industrial-grade conditions.
FRAM_NONFUNC_005 | Non-Functional | Maintainability should be a priority, with modular design and comprehensive documentation for ease of future updates and bug fixing. | Supporting easy updates to the system, modular approach for hardware and software upgrades, clear documentation of all dependencies.
Requirement ID | Category | Description
2.1.1 | Performance | Data Transfer Speed: Support I2C fast mode (400 kHz) or SPI (1 MHz). Operations should complete in 10ms for typical data blocks (64 bytes).
2.1.2 | Performance | Wake-Up Time: STM32 should wake up within 50ms from an interrupt or event.
2.1.3 | Performance | Power Consumption: Power consumption in low-power mode should not exceed 10µA.
2.2.1 | Reliability | Data Integrity: Use redundancy techniques (e.g., checksums) to prevent failures.
2.2.2 | Reliability | Communication Stability: Error rate should be below 0.01% over 10,000 read/write cycles.
2.2.3 | Reliability | Recovery from Failure: Automatically retry communication up to 3 times.
2.3.1 | Usability | User Feedback: Debug messages should be easy to interpret.
2.3.2 | Usability | Configurable Parameters: UART baud rate, I2C/SPI speed, and wake-up conditions should be configurable.
2.4.1 | Scalability | Memory Expansion: Support larger FRAM modules or multiple FRAM devices.
2.4.2 | Scalability | Adding New Peripherals: Design should allow easy integration of additional sensors or actuators.
2.5.1 | Security | Data Protection: Implement write-protection mechanisms for critical memory regions and optionally use authentication for sensitive areas.
2.5.2 | Security | Error Notification: Log security errors via UART and store them in non-volatile memory for analysis.
2.6.1 | Maintainability | Modular Code Design: Separate libraries for I2C/SPI communication, FRAM operations, power management, and debugging.
2.6.2 | Maintainability | Documentation: Provide extensive code documentation and user manuals.
2.6.3 | Maintainability | Code Reusability: Ensure the code is reusable for other STM32 projects.
2.7.1 | Environmental Constraints | Temperature and Humidity: Operate within 0°C to 70°C and under 20% to 80% relative humidity.
2.7.2 | Environmental Constraints | Shock and Vibration: Ensure the system is resistant to mild physical disturbances.
2.8.1 | Compliance | Communication Standards: Ensure I2C and SPI protocol compliance, including correct handling of clock stretching and synchronization.
2.8.2 | Compliance | Electrical Safety Standards: Follow safety and EMI regulations.
2.9.1 | Testability | Unit Testing: Each function should have unit tests, especially for communication protocols.
2.9.2 | Testability | System Testing: Test writing/reading to/from FRAM under different conditions.
2.9.3 | Testability | Test Mode: Implement a debug mode for simulating the system without FRAM hardware.
2.10.1 | Extensibility | New FRAM Modules: Support integration of additional or larger FRAM devices.
2.10.2 | Extensibility | New Features: Allow future enhancements like encryption or new sensors.

## Non-Functional Req
Non-Functional Requirements (Expanded)
2.1. Performance
| • | Data Transfer Speed:
| • | The system should support I2C fast mode (400 kHz) or SPI speeds up to 1 MHz for quick data transfers, reducing latency.
| • | Latency: Write and read operations should complete within 10ms for typical data blocks (e.g., 64 bytes).
| • | Wake-Up Time:
| • | The STM32 should wake up from sleep/stop modes within 50ms of receiving an interrupt or event.
| • | Power Consumption:
| • | Power consumption in low-power mode should not exceed 10µA to ensure energy efficiency when idle.
2.2. Reliability
| • | Data Integrity:
| • | The system should use redundancy techniques (e.g., data mirroring or checksums) to ensure data integrity in case of failures.
| • | A successful write operation should be guaranteed under normal operating conditions (temperature, voltage).
| • | Communication Stability:
| • | Communication with FRAM should have an error rate of less than 0.01% over 10,000 read/write cycles.
| • | Recovery from Failure:
| • | The system should automatically retry failed communication operations up to three times before flagging a hard error.
2.3. Usability
| • | User Feedback:
| • | Debugging messages over UART should be human-readable, well-formatted, and easy to interpret by a developer.
| • | Configurable Parameters:
| • | Allow configuration of key parameters such as UART baud rate, I2C/SPI clock speed, and wake-up conditions via a configuration file or by editing macros in the firmware.
2.4. Scalability
| • | Memory Expansion:
| • | The system should allow easy expansion to support larger FRAM modules or multiple FRAM devices via a modular address map.
| • | Adding New Peripherals:
| • | The system design should allow integration of additional sensors or actuators with minimal code changes (e.g., adding an external temperature sensor).
2.5. Security
| • | Data Protection:
| • | Implement write-protection mechanisms for critical memory regions within the FRAM. This ensures that sensitive data such as configuration parameters or system settings cannot be overwritten unless explicitly unlocked.
| • | Optionally implement authentication (using encryption or hashed passwords) to prevent unauthorized access to write functions in sensitive areas of memory.
| • | Error Notification:
| • | Security-related errors (such as unauthorized attempts to write to protected memory areas) should be logged over UART for debugging or further analysis.
| • | These security logs should also be stored in a non-volatile memory region (either FRAM or external memory) to allow for post-failure forensic analysis.
2.6. Maintainability
| • | Modular Code Design:
| • | The codebase should be structured in a modular way, with separate libraries for:
| • | I2C/SPI communication functions
| • | FRAM read/write operations
| • | Power management functions
| • | Debugging (UART) support
| • | This modular approach will allow easy replacement or upgrading of individual components without affecting the rest of the system.
| • | Documentation:
| • | The code should be extensively documented, with comments describing the purpose of each function, the data flow, and the communication process.
| • | A separate user manual or guide should be provided for future developers or users to modify the system (e.g., how to change I2C/SPI configurations, how to update the FRAM address map).
| • | Code Reusability:
| • | The code should be designed in a way that makes it reusable for other STM32 projects or memory interfaces. This could include the use of generic functions and configuration files.
2.7. Environmental Constraints
| • | Temperature and Humidity:
| • | The system should operate within a safe temperature range (e.g., 0°C to 70°C) and under typical indoor humidity levels (e.g., 20% to 80% relative humidity).
| • | Ensure that components, including STM32 and FRAM, are resistant to thermal stress (i.e., no data loss or corruption under operating conditions).
| • | Shock and Vibration:
| • | While not directly related to the software, the system should be robust enough to handle mild physical disturbances without losing power or corrupting data.
| • | Physical protection measures, such as shock-absorbing mounts for the PCB or enclosure, should be considered.
2.8. Compliance
| • | Communication Standards:
| • | Ensure that the system complies with industry-standard communication protocols:
| • | I2C protocol (as per NXP’s I2C specification), including multi-master configurations, clock stretching, and data packet sizes.
| • | SPI protocol compliance, including support for CPOL/CPHA settings and correct clock synchronization.
| • | Electrical Safety Standards:
| • | The design should follow electrical safety standards, especially regarding power consumption and electromagnetic interference (EMI), to ensure compliance with regulatory requirements.
2.9. Testability
| • | Unit Testing:
| • | Each function in the system (e.g., write_FRAM, read_FRAM) should have unit tests to verify its correct operation independently from the rest of the system.
| • | For communication functions (I2C/SPI), mock simulations should be implemented to simulate FRAM responses and validate the integrity of the code.
| • | System Testing:
| • | Complete end-to-end testing should be performed, including:
| • | Testing the STM32’s ability to write/read data to/from the FRAM under different conditions (varying power modes, different data sizes).
| • | Test cases for error handling (e.g., bus failure, no response from FRAM).
| • | Test Mode:
| • | Implement a debug/test mode where the system can be simulated without actual FRAM hardware, using dummy data or loopback connections to verify communication protocols.
2.10. Extensibility
| • | Adding New FRAM or Memory Modules:
| • | The system should allow for easy integration of additional FRAM modules (larger or multiple) by extending the addressing scheme.
| • | Software should support dynamic FRAM sizing, meaning that larger FRAM devices can be integrated without requiring substantial code rewrites.
| • | New Features:
| • | The design should be flexible enough to allow future enhancements, such as:
| • | Integrating encryption for secure data storage.
| • | Adding new sensors (e.g., temperature or pressure sensors) that store data directly into FRAM.
| • | Changing the communication interface from I2C/SPI to a faster or more robust protocol (e.g., CAN or UART-based memory access).
Summary of Expanded Requirements:
Non-Functional Requirements:
| 1. | Performance (speed, latency, power consumption).
| 2. | Reliability (data integrity, communication stability, error recovery).
| 3. | Usability (debugging, configuration flexibility).
| 4. | Scalability (expandability, modularity).
| 5. | Security (data protection, error notifications).
| 6. | Maintainability (modular code, documentation).
| 7. | Environmental Constraints (temperature, humidity, robustness).
| 8. | Compliance (communication and electrical standards).
| 9. | Testability (unit testing, system testing).
| 10. | Extensibility (support for future FRAM expansion and new features).

## System_Architecture
Write Operation to FRAM
1.1 User Input via UART
Trigger: User sends a write command via UART (e.g., WRITE 0x1234 [0xAA, 0xBB]).
Action by STM32:
1. The STM32's UART peripheral receives the command and triggers an interrupt or reads the input in a polling loop.
2. The STM32 decodes the received data. The command is parsed, extracting the memory address (0x1234) and the data block ([0xAA, 0xBB]).
3. Input validation is performed on the address and data (e.g., ensuring the data block size is valid for FRAM).
1.2 Address Validation
Check: The STM32 checks if the memory address (0x1234) falls within the valid range for the FRAM (e.g., 0x0000 to 0xFFFF).
If the address is invalid:
Error Response: The STM32 immediately logs the error (e.g., [ERROR] Invalid memory address 0x1234) and sends this error message over UART to the user.
The write operation is aborted.
If the address is valid:
Proceed: Continue to the next step.
1.3 Data Transfer Preparation
Step: Depending on the size of the data block and FRAM’s write capabilities, the STM32:
1. Prepares Data Chunks: If necessary, splits the data into multiple chunks for sequential transmission.
2. Protocol Configuration: Ensures the appropriate communication protocol (I2C or SPI) is set up.
1.4 Start I2C/SPI Communication with FRAM
Initiate: The STM32 initiates the I2C or SPI transfer, sending the command to write the data to FRAM:
1. Send Address: The STM32 sends the memory address (0x1234) to the FRAM.
2. Send Data: The STM32 transfers the data block ([0xAA, 0xBB]) over the I2C/SPI bus.
Error Handling: If a communication error occurs (e.g., bus failure, I2C/SPI not acknowledging):
1. The STM32 retries the operation up to a defined number of times.
2. If all retries fail, the STM32 logs the communication error (e.g., [ERROR] Write failed at address 0x1234) and sends this error message to the user via UART.
3. Abort further attempts if the error persists.
1.5 FRAM Acknowledgment
Wait for ACK: The STM32 waits for an acknowledgment from the FRAM, confirming the data has been written.
If ACK is received:
Proceed to the next step.
If ACK is not received:
Retry Mechanism: Retry the write operation as per the configured retry count.
Log Failure: If all retries fail, log the failure and inform the user (e.g., [ERROR] Write operation failed).
1.6 Completion of Write Operation
Confirmation: Once the data is successfully written:
1. The STM32 logs the write operation for debugging purposes (e.g., [INFO] Data written to FRAM at 0x1234: [0xAA, 0xBB]).
2. A success message is sent to the user over UART (e.g., [INFO] Write operation successful).
1.7 Return to Idle/Low-Power Mode
Transition: Once the write operation completes, the STM32 may:
1. Return to Idle: If no further tasks are pending.
2. Enter Low-Power Mode: If configured to conserve power during idle periods (more details below).
2. Read Operation from FRAM
2.1 User Input via UART
Trigger: User sends a read command via UART (e.g., READ 0x1234).
Action by STM32:
1. The STM32's UART peripheral receives the command, triggers an interrupt, or reads the input in a polling loop.
2. The STM32 parses the command to extract the memory address (0x1234).
2.2 Address Validation
Check: The STM32 checks if the requested address (0x1234) is within the FRAM's valid range.
If the address is invalid:
Error Response: The STM32 logs the error (e.g., [ERROR] Invalid address 0x1234) and informs the user via UART.
The read operation is aborted.
If the address is valid:
Proceed to the next step.
2.3 Initiate I2C/SPI Read from FRAM
Start Read Operation: The STM32 sends a read request to the FRAM via I2C/SPI, specifying the address (0x1234).
Error Handling: If the communication fails (e.g., no acknowledgment from FRAM):
Retry the read operation for a predefined number of times.
If all retries fail, log the error (e.g., [ERROR] Read failed at 0x1234) and notify the user via UART.
2.4 Retrieve Data from FRAM
Data Transfer: The STM32 retrieves the data block stored at the specified address from the FRAM.
If multiple bytes are requested, the STM32 continues fetching data until the required block is read.
2.5 Send Data to User via UART
Action: Once the data is successfully read, the STM32 sends the data block to the user via UART (e.g., [INFO] Data at 0x1234: [0xAA, 0xBB]).
2.6 Completion
The STM32 logs the successful read operation (e.g., [INFO] Read operation completed for 0x1234) and transitions back to idle or low-power mode.
3. Power Management and Low-Power Modes
3.1 Idle Detection
Trigger: The STM32 monitors system activity and detects when the system is idle (e.g., no UART commands, no ongoing I2C/SPI transactions).
3.2 Enter Low-Power Mode
Transition:
1. Disable Peripherals: The STM32 disables non-essential peripherals (e.g., UART, I2C/SPI clocks).
2. Power Module Control: The power management module puts the system into a low-power state to conserve energy.
3.3 Wake-Up Events
Trigger: The STM32 wakes up from low-power mode due to:
1. UART Command: A new command sent by the user over UART (interrupt-driven).
2. Timed Interrupt: A timer or external event signals the STM32 to wake up.
3.4 Exit Low-Power Mode
Transition:
1. Reinitialize Peripherals: The STM32 re-enables the UART, I2C/SPI interfaces, and other peripherals.
2. Resumes Operations: The STM32 resumes normal operation, ready for further commands or transactions.
3.5 Logging Power Status
Log: The STM32 logs the transition between power states (e.g., [INFO] Entering low-power mode or [INFO] Waking up from low-power mode) and sends updates over UART if logging is enabled.
4. Logging and Debugging via UART
Centralized Event Logging: The STM32 logs every critical operation (write/read success or failure, power state changes, etc.).
1. Store in Log Buffer: Logs are temporarily stored in a circular buffer or sent immediately via UART.
2. Real-Time Feedback: Users can receive real-time status updates about system operations over UART.
Error Handling: All errors, such as invalid addresses, communication timeouts, or failed operations, are logged and reported to the user with detailed error codes.
STM32 MCU
FRAM
SPI / I2C
Laptop
Power Module
SPI/ I2C
Watchdog

## Main_Architecture
Device drivers
Power Module
WDT
I2C
SPI